## Sheet1
| RISK MANAGEMENT LOG | [6 empty] | RISK MANAGEMENT LOG
Project Name | Car Purchasing Application
Project team Leader | Aml Mostafa
Project description | This platform will host an enormous database of cars enabling thesellers to advertise and market their cars and to help the buyer to search for their desired cars.
ID | Risk Impact | Probability of occurance | Risk Description | Project impact | Risk area | Responce strategy | contingency plan
Risk_001 | Medium | High | Current developers number is limited if any developer has an emergency situation or can't continue the project for any reason the project timeline will be affected. | Schedule may slip and possibly impact on the release date and work quality | Project Resources Budget Schedule | Find internal resource that meets required skill and be available through project timeline or increasing work load on current team members. | open hiring internal or external for the team or searching for a freelancer to complete the job.
Risk_002 | Low | Low | License for tools or OS may be expired and have to be renewed. | team can't continue their wok and the project schedule may slip and possibly restrict the accomplishment of project goals. | Project Resources Budget Schedule | The IT support team will renew the licenses. | Using another open source tool.
Risk_003 | High | Medium | The wrong estimation of the project time , the project effort and time is not enough to meet the project deadline . | If the time wasn't estimated properly, the project won't release with all the agreed features. | Budget Project release date | Ask the customer if the deadline can be extended to complete all features or release with current features. | The current team will work overtime to end all features.
Risk_004 | High | Medium | Client might change his mind to continue the project | Project will be stopped | Project Resources Budget Schedule | Discuss with the client the reasons why he wants to stop the project | The advance payment and/or contractual penalty placed in the contract.
Risk_005