## Sheet1
| RISK MANAGEMENT LOG | [6 empty] | RISK MANAGEMENT LOG
Project Name | Car Purchasing Application
Project team Leader | Nader Abdallah
Project description | This platform will host an enormous database of cars enabling thesellers to advertise and market their cars and to help the buyer to search for their desired cars.
ID | Risk Impact | Probability of occurance | Risk Description | Project impact | Risk area | Responce strategy | contingency plan
Risk_001 | Medium | High | Current developers number is limited if any developer has an emergency situation or can't continue the project for any reason the project timeline will be affected. | Schedule may slip and possibly impact on the release date and work quality | Project Resources Budget Schedule | Find internal resource that meets required skill and be available through project timeline or increasing work load on current team members. | open hiring internal or external for the team or searching for a freelancer to complete the job.
Risk_002 | Low | Low | License for tools or OS may be expired and have to be renewed. | team can't continue their wok and the project schedule may slip and possibly restrict the accomplishment of project goals. | Project Resources Budget Schedule | The IT support team will renew the licenses. | Using another open source tool.
Risk_003 | High | Medium | The wrong estimation of the project time , the project effort and time is not enough to meet the project deadline . | If the time wasn't estimated properly, the project won't release with all the agreed features. | Budget Project release date | Ask the customer if the deadline can be extended to complete all features or release with current features. | The current team will work overtime to end all features.
Risk_004 | High | Medium | Client might change his mind to continue the project | Project will be stopped | Project Resources Budget Schedule | Discuss with the client the reasons why he wants to stop the project | The advance payment and/or contractual penalty placed in the contract.
Risk_005 | High | Medium | The PM 'AML MOSTAFA' has been changed with a new PM' Nader ABDALLAH' | 1-Project progress wil be slowed and "Schedule may slip and possibly impact on the release date and work quality" 2-Communication issues: If the new project manager does not communicate effectively with team members or stakeholders, there may be misunderstandings or confusion about project goals, timelines, and priorities. | The whole project | 1-Smooth transition plan: Develop a transition plan to ensure a smooth handover from the previous project manager to the new project manager. This plan may include knowledge transfer sessions, documentation review, and introduction to key stakeholders. 2-Communication and alignment: Establish clear lines of communication with the new project manager and ensure they have a complete understanding of the project objectives, requirements, and constraints. Regular meetings and status updates can help in maintaining alignment and addressing any concerns or issues. 3-Monitor and evaluate: Continuously monitor the project progress and team dynamics under the new project manager. Regularly assess the effectiveness of the implemented strategies and make adjustments as necessary. | 1-Succession planning: Establish a succession plan that outlines the process for transferring project management responsibilities to another team member or a designated individual in case the new project manager is unable to continue in their role. This plan should include clear roles, responsibilities, and a smooth transition process. 2-Risk assessment and prioritization: Reassess project risks in light of the change in project manager and update their priorities accordingly. Identify high-impact risks and develop specific mitigation strategies to address them promptly. Decision-making authority: Clearly define decision-making authority within the project team, especially in the absence of the project manager. Establish a process for making critical decisions and ensure that key stakeholders are involved as necessary. Escalation procedures: Define escalation procedures in case critical issues arise that require immediate attention or intervention from higher management. Ensure that team members are aware of the escalation path and know when and how to escalate issues appropriately.