## Review
review TRACKER
Task | review COMMENT | reviewer | Status | date
PMP | -Goal part and validation strategy -RACI in Roles and responsibilities -Out of Scope part -Github Structure -CIL | Salma &Menna | Done | 2023-02-21
SRS | No comments | Beshoy | Done | 2023-02-21
SRS | -Schedule should be in one page. -we should select one font Times New Roman or Arial. -why font size 20. -in page11,all paragraph should be in one page | Beshoy | Done | 2023-03-09
UI | 1- landing page should be created. 2- logout button should be added in the home page. 3- number of available cars should be added down each car. | Menna | Done | 14/3/2023
Class diagram | Common functions beteen admin and user class should be in a seperate class and make the admin and user classes inheret from it. | Menna | Done | 15/3/2023
UI | -Cancel button should add in "add car"page according to the SRS. -Car details should be appeared in delete cars page. | Menna &Beshoy | Done | 15/3/2023
ERD | Status attribute should be added to the car | Eng. Mohamed Hassan | Done | 25/3/2023
Design Document | Generic diagrams such as wire frame and ERD should be prior to the specific ones | Amr | Done | 2023-07-04
Class Diagram | Classes should be created to mirror the actual classes within the code | Amr | Done | 2023-07-04
Flow charts | Flow charts should be created in a detailed way | Amr | Done | 2023-07-04
Design Document | Replace the actual front end with the wire frame | Amr | Done | 2023-07-04
SRS | 1. Add id to the alternative flows. 2. Add functional reqirments to "View car list". 3. Edit the output for delete and reserved car features. | Amr | Done | 27/4/2023
Review | Each task from the team , coach and Eng/ moahmed hassan should has review. | Amr |  | 2023-06-05
RTM | 1. update all use cases. 2. Add alternative flows from srs. | Amr |  | 2023-06-05
Design Document | Add ids to be reahable. | Amr |  | 2023-06-05
ERD | change "manage" relation to be add/delete. | Amr |  | 2023-06-05
Code Review | Change the prompt that appears to the user to be an alert + handle the cancel button in the alert. | Menna | Done | 2023-05-12