## CIL
CONFIGURATION ITEM LIST (CIL)
ID | File NAME | CL | VERSION | LOCATION Path (Github) | STATUS | DOCUMENTATION LINKS | Createtor 1 | Createtor 2 | Reviewer 1 | Reviewer 2
CIL_01 | SIQ | baseline | V.1.1 | Car-Purchasing-App/ 2- Reqs/ SIQ.xlsx | Confirmed | SIQ.xlsx | MENNA | SALMA | BESHO | FOUDA
CIL_02 | SRS | baseline | V.1.1 | Car-Purchasing-App/ 2- Reqs/ SRS V1.docx | Hold | SRS v1 | SALMA | MENNA | BESHO | AML
CIL_03 | PMP | baseline | V.1.0 | Car-Purchasing-App/ 1- PM/ PMP-Car Purchasing App.docx | Hold | PMP v1 | AML | BESHO | SALMA | MENNA
CIL_04 | Schedule | baseline | V.1.0 | Car-Purchasing-App/1- PM/schedule V1.0.xlsx | Hold | Schedule v1 | FOUDA | BESHO | AML | MENNA
CIL_05 | CIL | baseline | V.1.0 | /Car-Purchasing-App/1- PM/CIL V1.0.xlsx | Hold | https://github.com/beshoysamehsamaan/Car-Purchasing-App/blob/main/1-%20PM/CIL%20v1.xlsx | SALMA | MENNA | AML | FOUDA
CIL_06 | RTM | baseline | V.1.0 | Car-Purchasing-App/ 2- Reqs/ RTM v1.0.docx | Hold | RTM v1 | BESHO | AML | SALMA | None
CIL_07 | Risk Managment Plan | baseline | V.1.0 | Car-Purchasing-App/ 1- PM /project risk management V.1.0.docx | Hold | Risk Management Plan | AML | FOUDA | SALMA | BESHO
CIL_09 | Risk Managment Log | baseline | V.1.0 | Car-Purchasing-App/1- PM /Risk Management Log.xlsx | Hold | Risk Management Log | FOUDA | AML | SALMA | BESHO
CLICK HERE TO CREATE IN SMARTSHEET