## Review
Review TRACKER
Task | review COMMENT | reviewer | Status | date
PMP | -Goal part and validation strategy -RACI in Roles and responsibilities -Out of Scope part -Github Structure -CIL | Salma &Menna | Done | 2023-02-21
SRS | No comments | Beshoy | Done | 2023-02-21
SRS | -Schedule should be in one page. -we should select one font Times New Roman or Arial. -why font size 20. -in page11,all paragraph should be in one page | Beshoy | Done | 2023-03-09
UI | 1- landing page should be created. 2- logout button should be added in the home page. 3- number of available cars should be added down each car. | Menna | Done | 14/3/2023
Class diagram | Common functions beteen admin and user class should be in a seperate class and make the admin and user classes inheret from it. | Menna | Done | 15/3/2023
UI | -Cancel button should add in "add car"page according to the SRS. -Car details should be appeared in delete cars page. | Menna &Beshoy | Done | 15/3/2023
ERD | Status attribute should be added to the car | Eng. Mohamed Hassan | Done | 25/3/2023
Design Document | Generic diagrams such as wire frame and ERD should be prior to the specific ones | Amr | Done | 2023-07-04
Class Diagram | Classes should be created to mirror the actual classes within the code | Amr | Done | 2023-07-04
Flow charts | Flow charts should be created in a detailed way | Amr | Done | 2023-07-04
Design Document | Replace the actual front end with the wire frame | Amr | Done | 2023-07-04
SRS | 1. Add id to the alternative flows. 2. Add functional reqirments to "View car list". 3. Edit the output for delete and reserved car features. | Amr | Done | 27/4/2023
Review | Each task from the team , coach and Eng/ moahmed hassan should has review. | Amr | Done | 2023-06-05
RTM | 1. update all use cases. 2. Add alternative flows from srs. | Amr |  | 2023-06-05
Design Document | Add ids to be reahable. | Amr |  | 2023-06-05
ERD | change "manage" relation to be add/delete. | Amr | Done | 2023-06-05
Code Review | Change the prompt that appears to the user to be an alert + handle the cancel button in the alert. | Menna | Done | 2023-05-12
Change Analysis | add the action that 'll be taken for the risks that affect the the change that happened in the team in addition the the change that affected the code and the other documents. | salma + menna | Done | 2023-05-12
Change Analysis | be more specific especially in duration timeline. | Amr | Done | 2023-05-12
Test Plan | process for Test cases + bug report | Amr | Done | 2023-05-12