## Plan
Module | Assigned To | Estimated time | Actual time | Status | No. of Test Cases | No. of excuted Test Cases | Passed | Failed | Blocked | Coverage
Edit Customer | Moataz | 45 min | 60 min | Done | 32 | 0 | 0 | 1 |  | 0
Login Page | Moataz | 10 min | 20 min | Done | 15 | 15 | 9 | 0 | 6 | 100
Deposit | Kirolos | 15 min | 15 min | Done | 6 | 0 | 0 | 0 | 6 | 0
Withdrawal | Kirolos | 20 min | 15 min | Done | 7 | 0 | 0 | 0 | 7 | 0
Fund transfer | Kirolos | 20 min | 30 min | Done | 8 | 0 | 0 | 0 | 8 | 0
New customer | Bishoy | 45 min | 60 min | Done | 30 | 30 | 19 | 10 | 1 | 100
New Account | Nader | 15 min | 10 min | Done | 10 | 10 | 9 | 1 | 0 | 100
Balance Enquiry | Nader | 20 min | 15 min | Done | 8 | 8 | 6 | 2 | 0 | 100
customized statement | Nader | 20 min | 25 min | Done | 19 | 19 | 15 | 4 | 0 | 100
Change Password | Nader | 15 min | 15 min | Done | 9 | 9 | 7 | 2 | 0 | 100
Delete Account | Hosam | 15 min | 20 min | Done | 7 | 7 | 4 | 3 | 0 | 100
Delete Customer | Hosam | 15 min | 20 min | Done | 8 | 8 | 2 | 6 | 0 | 100
Mini Statement | Hosam | 20 min | 30 min | Done | 10 | 10 | 4 | 6 | 0 | 100
|  |  |  | Totals | 169 | 116 | 75 | 35 | 28 | 68.6391

## New Customer
____ | ____ | ID | Related Tech Requriments | Description | Type | PreConditions | Steps | Test Data | Designed By | Priority | Expected Result | Actual Result | attachment | Status
Add Customer Functionality for Manager | general | TC-ACFM-00 | happy scenario | Verfiy that Manger can Enter Add Customer | functional | 1- browser is availble 2- Login as manger sucessful | 1- Enter "Customer Name" in Customer Name field 2- Choose "Gender" in Gender field 3- choose "Date of Birth" in Date of Birth field 4- Enter "Address" in Address field 5- Enter "City" in City field 6- Enter "State" in State field 7- Enter "PIN" in PIN field 8- Enter "Mobile Number" in Mobile Number field 9- Enter "Email" in Email field 10- Press Submit button | 1- Customer Name = "Beshoy" 2- Gender = "male" 3- Date of Birth = "13-10-1998" 4- Address = "4 st xyzbn" 5- City = "cairo" 6- State = "egypt" 7- PIN = 123456 8- Mobile Number = "01221862730" 9- Email = "beshoysameh@gmail.com" | Beshoy | Medium | The system should accepts the input value and Add customer successfully | Connection failed: Access denied for user 'root'@'localhost' (using password: NO) | Screen Shot from Ui Desgin | blocked
| Customer Name | TC-ACFM-01 | 3.2-T4 | Verfiy that Manger can Enter Customer Name value with Numbers in Customer Name field | functional | 1- browser is availble 2- Login as manger sucessful | 1- Enter "Customer Name" in Customer Name field 2- Choose "Gender" in Gender field 3- choose "Date of Birth" in Date of Birth field 4- Enter "Address" in Address field 5- Enter "City" in City field 6- Enter "State" in State field 7- Enter "PIN" in PIN field 8- Enter "Mobile Number" in Mobile Number field 9- Enter "Email" in Email field 10- Press Submit button | 1- Customer Name = "Beshoy12" 2- Gender = "male" 3- Date of Birth = "13-10-1998" 4- Address = "4 st xyzbn" 5- City = "cairo" 6- State = "egypt" 7- PIN = 123456 8- Mobile Number = "01221862730" 9- Email = "beshoysameh@gmail.com" | Beshoy | Medium | system shows an error. | Numbers are not allowed | Screen Shot from Ui Desgin | pass
|  | TC-ACFM-02 | 3.2-T5 | Verfiy that Manger can Enter Customer Name value with special char in Customer Name field | functional | 1- browser is availble 2- Login as manger sucessful | 1- Enter "Customer Name" in Customer Name field 2- Choose "Gender" in Gender field 3- choose "Date of Birth" in Date of Birth field 4- Enter "Address" in Address field 5- Enter "City" in City field 6- Enter "State" in State field 7- Enter "PIN" in PIN field 8- Enter "Mobile Number" in Mobile Number field 9- Enter "Email" in Email field 10- Press Submit button | 1- Customer Name = "Beshoy@" 2- Gender = "male" 3- Date of Birth = "13-10-1998" 4- Address = "4 st xyzbn" 5- City = "cairo" 6- State = "egypt" 7- PIN = 123456 8- Mobile Number = "01221862730" 9- Email = "beshoysameh@gmail.com" | Beshoy | Medium | system shows an error. | Special characters are not allowed | Screen Shot from Ui Desgin | pass
|  | TC-ACFM-03 | 3.2-T6 | Verfiy that Manger can Leave Customer Name field blank | functional | 1- browser is availble 2- Login as manger sucessful | 1- Enter "Customer Name" in Customer Name field 2- Choose "Gender" in Gender field 3- choose "Date of Birth" in Date of Birth field 4- Enter "Address" in Address field 5- Enter "City" in City field 6- Enter "State" in State field 7- Enter "PIN" in PIN field 8- Enter "Mobile Number" in Mobile Number field 9- Enter "Email" in Email field 10- Press Submit button | 1- Customer Name = "" 2- Gender = "male" 3- Date of Birth = "13-10-1998" 4- Address = "4 st xyzbn" 5- City = "cairo" 6- State = "egypt" 7- PIN = 123456 8- Mobile Number = "01221862730" 9- Email = "beshoysameh@gmail.com" | Beshoy | Medium | system shows an error. | Customer name must not be blank | Screen Shot from Ui Desgin | pass
|  | TC-ACFM-04 | 3.2-T7 | Verfiy that Manger can Enter Customer Name value with space in first char in Customer Name field | functional | 1- browser is availble 2- Login as manger sucessful | 1- Enter "Customer Name" in Customer Name field 2- Choose "Gender" in Gender field 3- choose "Date of Birth" in Date of Birth field 4- Enter "Address" in Address field 5- Enter "City" in City field 6- Enter "State" in State field 7- Enter "PIN" in PIN field 8- Enter "Mobile Number" in Mobile Number field 9- Enter "Email" in Email field 10- Press Submit button | 1- Customer Name = " Beshoy" 2- Gender = "male" 3- Date of Birth = "13-10-1998" 4- Address = "4 st xyzbn" 5- City = "cairo" 6- State = "egypt" 7- PIN = 123456 8- Mobile Number = "01221862730" 9- Email = "beshoysameh@gmail.com" | Beshoy | Medium | system shows an error. | Numbers are not allowed ! | Screen Shot from Ui Desgin | fail
| address | TC-ACFM-05 | 3.2-T8 | Verfiy that Manger can Leave address field blank | functional | 1- browser is availble 2- Login as manger sucessful | 1- Enter "Customer Name" in Customer Name field 2- Choose "Gender" in Gender field 3- choose "Date of Birth" in Date of Birth field 4- Enter "Address" in Address field 5- Enter "City" in City field 6- Enter "State" in State field 7- Enter "PIN" in PIN field 8- Enter "Mobile Number" in Mobile Number field 9- Enter "Email" in Email field 10- Press Submit button | 1- Customer Name = "Beshoy" 2- Gender = "male" 3- Date of Birth = "13-10-1998" 4- Address = "" 5- City = "cairo" 6- State = "egypt" 7- PIN = 123456 8- Mobile Number = "01221862730" 9- Email = "beshoysameh@gmail.com" | Beshoy | Medium | system shows an error. | go to next page | Screen Shot from Ui Desgin | fail
|  | TC-ACFM-06 | 3.2-T9 | Verfiy that Manger can Enter address value with space in first char in address field | functional | 1- browser is availble 2- Login as manger sucessful | 1- Enter "Customer Name" in Customer Name field 2- Choose "Gender" in Gender field 3- choose "Date of Birth" in Date of Birth field 4- Enter "Address" in Address field 5- Enter "City" in City field 6- Enter "State" in State field 7- Enter "PIN" in PIN field 8- Enter "Mobile Number" in Mobile Number field 9- Enter "Email" in Email field 10- Press Submit button | 1- Customer Name = "Beshoy" 2- Gender = "male" 3- Date of Birth = "13-10-1998" 4- Address = " 4 st xyzbn" 5- City = "cairo" 6- State = "egypt" 7- PIN = 123456 8- Mobile Number = "01221862730" 9- Email = "beshoysameh@gmail.com" | Beshoy | Medium | system shows an error. | go to next page | Screen Shot from Ui Desgin | fail
|  | TC-ACFM-07 | 3.2-T10 | Verfiy that Manger can Enter address value with special char in address field | functional | 1- browser is availble 2- Login as manger sucessful | 1- Enter "Customer Name" in Customer Name field 2- Choose "Gender" in Gender field 3- choose "Date of Birth" in Date of Birth field 4- Enter "Address" in Address field 5- Enter "City" in City field 6- Enter "State" in State field 7- Enter "PIN" in PIN field 8- Enter "Mobile Number" in Mobile Number field 9- Enter "Email" in Email field 10- Press Submit button | 1- Customer Name = "Beshoy" 2- Gender = "male" 3- Date of Birth = "13-10-1998" 4- Address = " 4 @ st xyzbn" 5- City = "cairo" 6- State = "egypt" 7- PIN = 123456 8- Mobile Number = "01221862730" 9- Email = "beshoysameh@gmail.com" | Beshoy | Medium | system shows an error. | go to next page | Screen Shot from Ui Desgin | fail
| city | TC-ACFM-08 | 3.2-T13 | Verfiy that Manger can Enter city value with Numbers in city field | functional | 1- browser is availble 2- Login as manger sucessful | 1- Enter "Customer Name" in Customer Name field 2- Choose "Gender" in Gender field 3- choose "Date of Birth" in Date of Birth field 4- Enter "Address" in Address field 5- Enter "City" in City field 6- Enter "State" in State field 7- Enter "PIN" in PIN field 8- Enter "Mobile Number" in Mobile Number field 9- Enter "Email" in Email field 10- Press Submit button | 1- Customer Name = "Beshoy" 2- Gender = "male" 3- Date of Birth = "13-10-1998" 4- Address = "4 st xyzbn" 5- City = "cairo23" 6- State = "egypt" 7- PIN = 123456 8- Mobile Number = "01221862730" 9- Email = "beshoysameh@gmail.com" | Beshoy | Medium | system shows an error. | Numbers are not allowed | Screen Shot from Ui Desgin | pass
|  | TC-ACFM-09 | 3.2-T11 | Verfiy that Manger can Enter city value with special char in city field | functional | 1- browser is availble 2- Login as manger sucessful | 1- Enter "Customer Name" in Customer Name field 2- Choose "Gender" in Gender field 3- choose "Date of Birth" in Date of Birth field 4- Enter "Address" in Address field 5- Enter "City" in City field 6- Enter "State" in State field 7- Enter "PIN" in PIN field 8- Enter "Mobile Number" in Mobile Number field 9- Enter "Email" in Email field 10- Press Submit button | 1- Customer Name = "Beshoy" 2- Gender = "male" 3- Date of Birth = "13-10-1998" 4- Address = "4 st xyzbn" 5- City = "cairo@" 6- State = "egypt" 7- PIN = 123456 8- Mobile Number = "01221862730" 9- Email = "beshoysameh@gmail.com" | Beshoy | Medium | system shows an error. | Special characters are not allowed | Screen Shot from Ui Desgin | pass
|  | TC-ACFM-10 | 3.2-T12 | Verfiy that Manger can Leave city field blank | functional | 1- browser is availble 2- Login as manger sucessful | 1- Enter "Customer Name" in Customer Name field 2- Choose "Gender" in Gender field 3- choose "Date of Birth" in Date of Birth field 4- Enter "Address" in Address field 5- Enter "City" in City field 6- Enter "State" in State field 7- Enter "PIN" in PIN field 8- Enter "Mobile Number" in Mobile Number field 9- Enter "Email" in Email field 10- Press Submit button | 1- Customer Name = "Beshoy" 2- Gender = "male" 3- Date of Birth = "13-10-1998" 4- Address = "4 st xyzbn" 5- City = "" 6- State = "egypt" 7- PIN = 123456 8- Mobile Number = "01221862730" 9- Email = "beshoysameh@gmail.com" | Beshoy | Medium | system shows an error. | City Field must be not blank | Screen Shot from Ui Desgin | pass
|  | TC-ACFM-11 | 3.2-T14 | Verfiy that Manger can Enter city value with space in first char in city field | functional | 1- browser is availble 2- Login as manger sucessful | 1- Enter "Customer Name" in Customer Name field 2- Choose "Gender" in Gender field 3- choose "Date of Birth" in Date of Birth field 4- Enter "Address" in Address field 5- Enter "City" in City field 6- Enter "State" in State field 7- Enter "PIN" in PIN field 8- Enter "Mobile Number" in Mobile Number field 9- Enter "Email" in Email field 10- Press Submit button | 1- Customer Name = " Beshoy" 2- Gender = "male" 3- Date of Birth = "13-10-1998" 4- Address = "4 st xyzbn" 5- City = " cairo" 6- State = "egypt" 7- PIN = 123456 8- Mobile Number = "01221862730" 9- Email = "beshoysameh@gmail.com" | Beshoy | Medium | system shows an error. | Numbers are not allowed ! | Screen Shot from Ui Desgin | fail
| state | TC-ACFM-012 | 3.2-T15 | Verfiy that Manger can Enter state value with Numbers in state field | functional | 1- browser is availble 2- Login as manger sucessful | 1- Enter "Customer Name" in Customer Name field 2- Choose "Gender" in Gender field 3- choose "Date of Birth" in Date of Birth field 4- Enter "Address" in Address field 5- Enter "City" in City field 6- Enter "State" in State field 7- Enter "PIN" in PIN field 8- Enter "Mobile Number" in Mobile Number field 9- Enter "Email" in Email field 10- Press Submit button | 1- Customer Name = "Beshoy" 2- Gender = "male" 3- Date of Birth = "13-10-1998" 4- Address = "4 st xyzbn" 5- City = "cairo" 6- State = "egypt12" 7- PIN = 123456 8- Mobile Number = "01221862730" 9- Email = "beshoysameh@gmail.com" | Beshoy | Medium | system shows an error. | Numbers are not allowed | Screen Shot from Ui Desgin | pass
|  | TC-ACFM-13 | 3.2-T17 | Verfiy that Manger can Enter state value with special char in state field | functional | 1- browser is availble 2- Login as manger sucessful | 1- Enter "Customer Name" in Customer Name field 2- Choose "Gender" in Gender field 3- choose "Date of Birth" in Date of Birth field 4- Enter "Address" in Address field 5- Enter "City" in City field 6- Enter "State" in State field 7- Enter "PIN" in PIN field 8- Enter "Mobile Number" in Mobile Number field 9- Enter "Email" in Email field 10- Press Submit button | 1- Customer Name = "Beshoy" 2- Gender = "male" 3- Date of Birth = "13-10-1998" 4- Address = "4 st xyzbn" 5- City = "cairo" 6- State = "egypt@" 7- PIN = 123456 8- Mobile Number = "01221862730" 9- Email = "beshoysameh@gmail.com" | Beshoy | Medium | system shows an error. | Special characters are not allowed | Screen Shot from Ui Desgin | pass
|  | TC-ACFM-14 | 3.2-T16 | Verfiy that Manger can Leave state field blank | functional | 1- browser is availble 2- Login as manger sucessful | 1- Enter "Customer Name" in Customer Name field 2- Choose "Gender" in Gender field 3- choose "Date of Birth" in Date of Birth field 4- Enter "Address" in Address field 5- Enter "City" in City field 6- Enter "State" in State field 7- Enter "PIN" in PIN field 8- Enter "Mobile Number" in Mobile Number field 9- Enter "Email" in Email field 10- Press Submit button | 1- Customer Name = "Beshoy" 2- Gender = "male" 3- Date of Birth = "13-10-1998" 4- Address = "4 st xyzbn" 5- City = "Cairo" 6- State = "" 7- PIN = 123456 8- Mobile Number = "01221862730" 9- Email = "beshoysameh@gmail.com" | Beshoy | Medium | system shows an error. | State must not be blank | Screen Shot from Ui Desgin | pass
|  | TC-ACFM-15 | 3.2-T17.1 | Verfiy that Manger can Enter state value with space in first char in state field | functional | 1- browser is availble 2- Login as manger sucessful | 1- Enter "Customer Name" in Customer Name field 2- Choose "Gender" in Gender field 3- choose "Date of Birth" in Date of Birth field 4- Enter "Address" in Address field 5- Enter "City" in City field 6- Enter "State" in State field 7- Enter "PIN" in PIN field 8- Enter "Mobile Number" in Mobile Number field 9- Enter "Email" in Email field 10- Press Submit button | 1- Customer Name = " Beshoy" 2- Gender = "male" 3- Date of Birth = "13-10-1998" 4- Address = "4 st xyzbn" 5- City = "cairo" 6- State = " egypt" 7- PIN = 123456 8- Mobile Number = "01221862730" 9- Email = "beshoysameh@gmail.com" | Beshoy | Medium | system shows an error. | Numbers are not allowed ! | Screen Shot from Ui Desgin | fail
| PIN | TC-ACFM-016 | 3.2-T18 | Verfiy that Manger can Enter pin value with char in pin field | functional | 1- browser is availble 2- Login as manger sucessful | 1- Enter "Customer Name" in Customer Name field 2- Choose "Gender" in Gender field 3- choose "Date of Birth" in Date of Birth field 4- Enter "Address" in Address field 5- Enter "City" in City field 6- Enter "State" in State field 7- Enter "PIN" in PIN field 8- Enter "Mobile Number" in Mobile Number field 9- Enter "Email" in Email field 10- Press Submit button | 1- Customer Name = "Beshoy" 2- Gender = "male" 3- Date of Birth = "13-10-1998" 4- Address = "4 st xyzbn" 5- City = "cairo" 6- State = "egypt" 7- PIN = 1234bs 8- Mobile Number = "01221862730" 9- Email = "beshoysameh@gmail.com" | Beshoy | Medium | system shows an error. | Characters are not allowed | Screen Shot from Ui Desgin | pass
|  | TC-ACFM-17 | 3.2-T20 | Verfiy that Manger can Enter pin value with special char in pin field | functional | 1- browser is availble 2- Login as manger sucessful | 1- Enter "Customer Name" in Customer Name field 2- Choose "Gender" in Gender field 3- choose "Date of Birth" in Date of Birth field 4- Enter "Address" in Address field 5- Enter "City" in City field 6- Enter "State" in State field 7- Enter "PIN" in PIN field 8- Enter "Mobile Number" in Mobile Number field 9- Enter "Email" in Email field 10- Press Submit button | 1- Customer Name = "Beshoy" 2- Gender = "male" 3- Date of Birth = "13-10-1998" 4- Address = "4 st xyzbn" 5- City = "cairo" 6- State = "egypt" 7- PIN = 1234@56 8- Mobile Number = "01221862730" 9- Email = "beshoysameh@gmail.com" | Beshoy | Medium | system shows an error. | Special characters are not allowed | Screen Shot from Ui Desgin | pass
|  | TC-ACFM-18 | 3.2-T19 | Verfiy that Manger can Leave pin field blank | functional | 1- browser is availble 2- Login as manger sucessful | 1- Enter "Customer Name" in Customer Name field 2- Choose "Gender" in Gender field 3- choose "Date of Birth" in Date of Birth field 4- Enter "Address" in Address field 5- Enter "City" in City field 6- Enter "State" in State field 7- Enter "PIN" in PIN field 8- Enter "Mobile Number" in Mobile Number field 9- Enter "Email" in Email field 10- Press Submit button | 1- Customer Name = "Beshoy" 2- Gender = "male" 3- Date of Birth = "13-10-1998" 4- Address = "4 st xyzbn" 5- City = "Cairo" 6- State = "egypt" 7- PIN = 8- Mobile Number = "01221862730" 9- Email = "beshoysameh@gmail.com" | Beshoy | Medium | system shows an error. | PIN Code must not be blank | Screen Shot from Ui Desgin | pass
|  | TC-ACFM-19 | 3.2-T22 | Verfiy that Manger can Enter pin value with space in first char in pin field | functional | 1- browser is availble 2- Login as manger sucessful | 1- Enter "Customer Name" in Customer Name field 2- Choose "Gender" in Gender field 3- choose "Date of Birth" in Date of Birth field 4- Enter "Address" in Address field 5- Enter "City" in City field 6- Enter "State" in State field 7- Enter "PIN" in PIN field 8- Enter "Mobile Number" in Mobile Number field 9- Enter "Email" in Email field 10- Press Submit button | 1- Customer Name = " Beshoy" 2- Gender = "male" 3- Date of Birth = "13-10-1998" 4- Address = "4 st xyzbn" 5- City = "cairo" 6- State = "egypt" 7- PIN = " 123456" 8- Mobile Number = "01221862730" 9- Email = "beshoysameh@gmail.com" | Beshoy | Medium | system shows an error. | move to next page | Screen Shot from Ui Desgin | fail
|  | TC-ACFM-20 | 3.2-T21 | Verfiy that Manger can Enter pin > 6 in pin field | functional | 1- browser is availble 2- Login as manger sucessful | 1- Enter "Customer Name" in Customer Name field 2- Choose "Gender" in Gender field 3- choose "Date of Birth" in Date of Birth field 4- Enter "Address" in Address field 5- Enter "City" in City field 6- Enter "State" in State field 7- Enter "PIN" in PIN field 8- Enter "Mobile Number" in Mobile Number field 9- Enter "Email" in Email field 10- Press Submit button | 1- Customer Name = "Beshoy" 2- Gender = "male" 3- Date of Birth = "13-10-1998" 4- Address = "4 st xyzbn" 5- City = "cairo" 6- State = "egypt" 7- PIN = "12345678" 8- Mobile Number = "01221862730" 9- Email = "beshoysameh@gmail.com" | Beshoy | Medium | system shows an error. | not allowed | Screen Shot from Ui Desgin | pass
|  | TC-ACFM-21 | 3.2-T21 | Verfiy that Manger can Enter pin < 6 in pin field | functional | 1- browser is availble 2- Login as manger sucessful | 1- Enter "Customer Name" in Customer Name field 2- Choose "Gender" in Gender field 3- choose "Date of Birth" in Date of Birth field 4- Enter "Address" in Address field 5- Enter "City" in City field 6- Enter "State" in State field 7- Enter "PIN" in PIN field 8- Enter "Mobile Number" in Mobile Number field 9- Enter "Email" in Email field 10- Press Submit button | 1- Customer Name = "Beshoy" 2- Gender = "male" 3- Date of Birth = "13-10-1998" 4- Address = "4 st xyzbn" 5- City = "cairo" 6- State = "egypt" 7- PIN = "1234" 8- Mobile Number = "01221862730" 9- Email = "beshoysameh@gmail.com" | Beshoy | Medium | system shows an error. | PIN Code must have 6 Digits | Screen Shot from Ui Desgin | pass
| Telephone Number | TC-ACFM-22 | 3.2-T25 | Verfiy that Manger can Enter telephone number value with char in telephone numbe field | functional | 1- browser is availble 2- Login as manger sucessful | 1- Enter "Customer Name" in Customer Name field 2- Choose "Gender" in Gender field 3- choose "Date of Birth" in Date of Birth field 4- Enter "Address" in Address field 5- Enter "City" in City field 6- Enter "State" in State field 7- Enter "PIN" in PIN field 8- Enter "Mobile Number" in Mobile Number field 9- Enter "Email" in Email field 10- Press Submit button | 1- Customer Name = "Beshoy" 2- Gender = "male" 3- Date of Birth = "13-10-1998" 4- Address = "4 st xyzbn" 5- City = "cairo" 6- State = "egypt" 7- PIN = 123456 8- Mobile Number = "01221862730BB" 9- Email = "beshoysameh@gmail.com" | Beshoy | Medium | system shows an error. | Characters are not allowed | Screen Shot from Ui Desgin | pass
|  | TC-ACFM-23 | 3.2-T24 | Verfiy that Manger can Enter telephone numbe value with special char in telephone numbe field | functional | 1- browser is availble 2- Login as manger sucessful | 1- Enter "Customer Name" in Customer Name field 2- Choose "Gender" in Gender field 3- choose "Date of Birth" in Date of Birth field 4- Enter "Address" in Address field 5- Enter "City" in City field 6- Enter "State" in State field 7- Enter "PIN" in PIN field 8- Enter "Mobile Number" in Mobile Number field 9- Enter "Email" in Email field 10- Press Submit button | 1- Customer Name = "Beshoy" 2- Gender = "male" 3- Date of Birth = "13-10-1998" 4- Address = "4 st xyzbn" 5- City = "cairo" 6- State = "egypt" 7- PIN = 123456 8- Mobile Number = "@01221862730" 9- Email = "beshoysameh@gmail.com" | Beshoy | Medium | system shows an error. | Special characters are not allowed | Screen Shot from Ui Desgin | pass
|  | TC-ACFM-24 | 3.2-T23 | Verfiy that Manger can Leave telephone numbe field blank | functional | 1- browser is availble 2- Login as manger sucessful | 1- Enter "Customer Name" in Customer Name field 2- Choose "Gender" in Gender field 3- choose "Date of Birth" in Date of Birth field 4- Enter "Address" in Address field 5- Enter "City" in City field 6- Enter "State" in State field 7- Enter "PIN" in PIN field 8- Enter "Mobile Number" in Mobile Number field 9- Enter "Email" in Email field 10- Press Submit button | 1- Customer Name = "Beshoy" 2- Gender = "male" 3- Date of Birth = "13-10-1998" 4- Address = "4 st xyzbn" 5- City = "Cairo" 6- State = "egypt" 7- PIN = 123456 8- Mobile Number = "" 9- Email = "beshoysameh@gmail.com" | Beshoy | Medium | system shows an error. | Telephone no must not be blank | Screen Shot from Ui Desgin | pass
|  | TC-ACFM-25 | 3.2-T26 | Verfiy that Manger can Enter telephone numbe value with space in first char in telephone numbe field | functional | 1- browser is availble 2- Login as manger sucessful | 1- Enter "Customer Name" in Customer Name field 2- Choose "Gender" in Gender field 3- choose "Date of Birth" in Date of Birth field 4- Enter "Address" in Address field 5- Enter "City" in City field 6- Enter "State" in State field 7- Enter "PIN" in PIN field 8- Enter "Mobile Number" in Mobile Number field 9- Enter "Email" in Email field 10- Press Submit button | 1- Customer Name = " Beshoy" 2- Gender = "male" 3- Date of Birth = "13-10-1998" 4- Address = "4 st xyzbn" 5- City = "cairo" 6- State = "egypt" 7- PIN = "123456" 8- Mobile Number = " 01221862730" 9- Email = "beshoysameh@gmail.com" | Beshoy | Medium | system shows an error. | move to next page | Screen Shot from Ui Desgin | fail
| email | TC-ACFM-26 | 3.2-T27 | Verfiy that Manger can Leave email field blank | functional | 1- browser is availble 2- Login as manger sucessful | 1- Enter "Customer Name" in Customer Name field 2- Choose "Gender" in Gender field 3- choose "Date of Birth" in Date of Birth field 4- Enter "Address" in Address field 5- Enter "City" in City field 6- Enter "State" in State field 7- Enter "PIN" in PIN field 8- Enter "Mobile Number" in Mobile Number field 9- Enter "Email" in Email field 10- Press Submit button | 1- Customer Name = "Beshoy" 2- Gender = "male" 3- Date of Birth = "13-10-1998" 4- Address = "4 st xyzbn" 5- City = "Cairo" 6- State = "egypt" 7- PIN = 123456 8- Mobile Number = "01221862730" 9- Email = "" | Beshoy | Medium | system shows an error. | Email-ID must not be blank | Screen Shot from Ui Desgin | pass
|  | TC-ACFM-27 | 3.2-T29 | Verfiy that Manger can Enter email value with space in first char in email field | functional | 1- browser is availble 2- Login as manger sucessful | 1- Enter "Customer Name" in Customer Name field 2- Choose "Gender" in Gender field 3- choose "Date of Birth" in Date of Birth field 4- Enter "Address" in Address field 5- Enter "City" in City field 6- Enter "State" in State field 7- Enter "PIN" in PIN field 8- Enter "Mobile Number" in Mobile Number field 9- Enter "Email" in Email field 10- Press Submit button | 1- Customer Name = "Beshoy" 2- Gender = "male" 3- Date of Birth = "13-10-1998" 4- Address = "4 st xyzbn" 5- City = "cairo" 6- State = "egypt" 7- PIN = "123456" 8- Mobile Number = "01221862730" 9- Email = " beshoysameh@gmail.com" | Beshoy | Medium | system shows an error. | move to next page | Screen Shot from Ui Desgin | fail
|  | TC-ACFM-28 | 3.3-F33 | Verfiy that Manger can Enter email value and id is exist in sys | functional | 1- browser is availble 2- Login as manger sucessful | 1- Enter "Customer Name" in Customer Name field 2- Choose "Gender" in Gender field 3- choose "Date of Birth" in Date of Birth field 4- Enter "Address" in Address field 5- Enter "City" in City field 6- Enter "State" in State field 7- Enter "PIN" in PIN field 8- Enter "Mobile Number" in Mobile Number field 9- Enter "Email" in Email field 10- Press Submit button | 1- Customer Name = "Beshoy" 2- Gender = "male" 3- Date of Birth = "13-10-1998" 4- Address = "4 st xyzbn" 5- City = "cairo" 6- State = "egypt" 7- PIN = "123456" 8- Mobile Number = "01221862730" 9- Email = " moataz@gmail.com" | Beshoy | Medium | system shows an error. | move to next page | Screen Shot from Ui Desgin | fail
|  | TC-ACFM-29 | 3.2-T28 | Verfiy that Manger can Enter email value with not valid format (without @ .com ) | functional | 1- browser is availble 2- Login as manger sucessful | 1- Enter "Customer Name" in Customer Name field 2- Choose "Gender" in Gender field 3- choose "Date of Birth" in Date of Birth field 4- Enter "Address" in Address field 5- Enter "City" in City field 6- Enter "State" in State field 7- Enter "PIN" in PIN field 8- Enter "Mobile Number" in Mobile Number field 9- Enter "Email" in Email field 10- Press Submit button | 1- Customer Name = "Beshoy" 2- Gender = "male" 3- Date of Birth = "13-10-1998" 4- Address = "4 st xyzbn" 5- City = "cairo" 6- State = "egypt" 7- PIN = "123456" 8- Mobile Number = "01221862730" 9- Email = " beshoysamehgmail" | Beshoy | Medium | system shows an error. | Email-ID is not valid | Screen Shot from Ui Desgin | pass

## Add Car
____ | ____ | ID | Related Requriments (SRS) | Description | Type | PreConditions | Steps | Designed By | Priority | Expected Result | Actual Result | attachment | Status
| General | TC-AddCar-00 | REQ-6 | Verify that a car can be added successfully by an admin. | functional | 1- browser is available 2- Login as admin successfully | 1. Press "add button" in home page. 2. Upload a photo. 3. Choose " toyota" from brand dropdown list . 4. Choose " Toyota " from car model dropdown list. 5.Fill in "500,000" in the price field. 6. Fill in " Hello " in the description field. 7. Click on the "Save" button | Salma | High | 1. The car should be added successfully. 2. A success message should be displayed indicating that the car has been added "car added successfullly". 3. The added car should be displayed in the car list on the home page for the admin and customer .
| Description field | TC-AddCar- Description-01 | T031, T032 | Verify that an error message will be displayed for the Admin when the description field is left blank. | technical | 1- browser is available 2- Login as admin successfully | 1. Press "add button" in home page. 2. Upload a photo. 3. Choose " toyota" from brand dropdown list . 4. Choose " Toyota " from car model dropdown list. 5.Fill in "500,000" in the price field. 6.Fill in " " in description field 7. Click on the "Save" button | Salma | High | 1. An error message "Please fill out this field" should be displayed. 2. The car should not be added to the car list on the home page.
| Price Field | TC-AddCar- Price-02 | T030, T032 | Verify that an error message will be displayed for the Admin when the price field is left blank. | technical | 1- browser is available 2- Login as admin successfully | 1. Press "add button" in home page. 2. Upload a photo. 3. Choose " toyota" from brand dropdown list . 4. Choose " Toyota " from car model dropdown list. 5.Fill in " " in the price field. 6. Fill in " Hello " the description field. 7. Click on the "Save" button | Salma | High | 1. An error message "Please fill out this field" should be displayed. 2. The car should not be added to the car list on the home page.
|  | TC-AddCar- Price-03 | T028 | Verify that the price field doesn't accept special charchters. | technical | 1- browser is available 2- Login as admin successfully | 1. Press "add button" in home page. 2. Upload a photo. 3. Choose " toyota" from brand dropdown list . 4. Choose " Toyota " from car model dropdown list. 5.Fill in "%$## in the price field. 6. Fill in " Hello " the description field. 7. Click on the "Save" button | Salma | High | 1. The price field shoudln't accept special characters. 2. The car should not be added to the car list on the home page.
| Alternative flow | TC-AddCar- Cancel-04 | 6.1 | Verify that an admin can cancel adding a car. | functional | 1- browser is available 2- Login as admin successfully | 1. Press "add button" in home page. 2. Upload a photo. 3. Choose " toyota" from brand dropdown list . 4. Choose " Toyota " from car model dropdown list. 5.Fill in "500,000" in the price field. 6. Fill in " Hello " in the description field. 7. Click on the "Cancel" button | Beshoy | Medium | 1. The home page should be displayed. 2. The car should not be added to the car list on the home page.
| Customer | TC-AddCar- User-04 | REQ-6 | verify that the car has been added to the user successfully to his home page. |  | 1- browser is available | 1. Open the login page. 2. Fill in :salma@gmail.com" in email field. 3. Fill in " *********" in the password field 4.Click on the "Login" button. 5. Check that the car is added to the home page. |  |  | The car with its details, that the admin already added, should be displayed on the user's home page.

## Delete car
____ | ____ | ID | Related Requriments (SRS) | Description | Type | PreConditions | Steps | Designed By | Priority | Expected Result | Actual Result | attachment | Status
| General | TC-DelCar-00 | REQ-7 | Verify that an admin can delete a car successfully | functional | 1- browser is available 2- Login as admin successfully | 1. Choose one of the available cars on the home page. 2. Click on the "Delete" button for that car. | Salma | High | 1. The car should be deleted successfully. 2. A success message should be displayed in new page indicating that the car has been deleted successfully "Car is deleted successfully in new page". 3. The deleted car should not be displayed in the car list on the home page for admin and user.
| Customer | TC-DelCar- User-04 | REQ-7 | verify that the car has been deleted from the user's home page. |  | 1- browser is available | 1. Open the login page. 2. Fill in :salma@gmail.com" in email field. 3. Fill in " *********" in the password field 4.Click on the "Login" button. 5. Check that the car is deleted from the home page. |  |  | The car with its details, that the admin already added, should be deleted from the user's home page.

## View Car
____ | ____ | ID | Related Requriments (SRS) | Description | Type | PreConditions | Steps | Designed By | Priority | Expected Result | Actual Result | attachment | Status
| General | TC-HomePage-00 | REQ-4 | Verify that the Home Page displays all unreserved cars in the database with their details and reserve button. | functional | 1- browser is available 2- Login as user successfully | 1.Check that all unreserved cars in the database are displayed on the home page. 2. Verify that the following information is displayed for each car: photo, price, brand, model, description, and reserve button. | Salma | High | All unreserved cars in the database are displayed on the Home Page with their details and reserve button below each one.

## search
____ | ID | Related Requriments (SRS) | Description | Type | PreConditions | Steps | Designed By | Priority | Expected Result | Actual Result | attachment | Status
Price Field | TC-SearchBrand-00 | REQ-5 | Verify if the user can search for cars by brand name. | functional | 1- browser is available 2- Login as user successfully | 1. Click on the search bar. 2. Enter "toyota " in the search bar. 3. Click on the search button. . | Salma | High | The system should display a list of cars that match the toyota brand.
| TC-AddCar- Price-03 | REQ-5 | Verify that user sees a pop-up message when there are no cars available for the entered brand name. | technical | 1- browser is available 2- Login as admin successfully | 1. Click on the search bar. 2. Enter "toyota " in the search bar. 3. Click on the search button. . | Salma | High | 1. The price field shoudln't accept special characters. 2. The car should not be added to the car list on the home page.

## login
lo

## Logout
L