## Sheet1
ID | DESCRIPTION | RISKS | IMPACT | ACTIONS
Change_Request1 | change in the team Lead" from Aml Mansour to Nader Abdallah" | 1- need to hand over all the cuurent tasks 2-Need to spend more time to make the new lead get familiar with the project | 1-spending extra time in training the new member 2- spending time in reassign any uncompleted tasks issued to the old member | 1-Conducted meetings with the new lead to explain to him the overall system , required features , workflow 2- re-assigned PMP , risk management log and test plan document and review tracker update and RACI
Change_Request2 | Customer required an update in the reservition feature for the car | 1-The addition of a new feature may impact the project timeline and resources, potentially leading to delays in other project deliverables. 2- Introducing changes to the reservation feature might result in compatibility issues with existing systems or components, requiring additional development and testing efforts. | 1-The inclusion of the new reservation feature may extend the project timeline, affecting the overall project schedule and potentially delaying other planned activities. 2-Additional development, testing, and deployment efforts will be required to implement and validate the new feature, potentially impacting resource allocation and availability for other project tasks. 3-the new change will require updates in many document like(PMP , RTM , UI Design , SRS , Code , Testing), | assigned the new change to our back end development team (Beshoy & Menna) and assigned the new test activity to salma
Change_Request3