## Car Purchasing
Car Purchasing | [9 empty] | Smartsheet Tip ➜ | [6 empty] | A Gantt chart's visual timeline allows you to see details about each task as well as project dependencies.
PROJECT TITLE |  | Car Purchasing | [7 empty] | COMPANY NAME | [7 empty] | ITI
PROJECT MANAGER |  | Aml | [7 empty] | DATE | [7 empty] | 2023-03-12
WBS NUMBER | TASK TITLE | TASK OWNER | TASK SUP | TASK REVIEW | TASK REVIEW SUP | START DATE | DUE DATE | DURATION | PCT OF TASK COMPLETE | PHASE ONE | [15 empty] | PHASE TWO
[10 empty] | WEEK 1 | [5 empty] | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6
[10 empty] | S | S | M | T | W | T | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F
1 | Project Managment
1.1 | Project Managment Plan | AML | BESHO | SALMA | MENNA | 2023-02-18 | 2023-02-23 | 5 | 100% | WEEK 1 S: problem; WEEK 1 S: problem; WEEK 1 M: in progress; WEEK 1 T: in progress; WEEK 1 W: in progress; WEEK 1 T: Done
1.1.1 | Risk Management | FOUDA | AML | BESHO | SALMA | 2023-02-22 | 2023-02-23 | 1 | 100% | WEEK 1 T: in progress; WEEK 1 W: in progress; WEEK 1 T: Done
1.2 | Research | AML | MENNA | SALMA | FOUDA | 2023-02-18 | 2023-02-23 | 5 | 90% | WEEK 1 S: in progress; WEEK 1 S: in progress; WEEK 1 M: in progress; WEEK 1 T: in progress; WEEK 1 W: in progress; WEEK 1 T: Done
1.3 | Schedule and progress report | FOUDA | BESHO | MENNA | AML | 2023-02-18 | 2023-02-23 | 5 | 95% | WEEK 1 S: problem; WEEK 1 S: in progress; WEEK 1 M: in progress; WEEK 1 T: in progress; WEEK 1 W: in progress; WEEK 1 T: Done
1.4 | Communication Managment | AML | BESHO | SALMA | MENNA | 2023-02-18 | 2023-02-19 | 1 | 100% | WEEK 1 S: in progress; WEEK 1 S: Done
1.5 | CIL | SALMA | MENNA | AML | FOUDA | 2023-02-23 | 2023-02-23 | 0 | 100% | WEEK 1 T: Done
1.7 | Configuration Managment Setup | BESHO | MENNA | AML | SALMA | 2023-02-20 | 2023-02-20 | 0 | 100% | WEEK 1 M: Done
2 | Requirements
2.2.1 | SRS | MENNA | SALMA | BESHO | AML | 2023-02-19 | 2023-02-22 | 3 | 100% | WEEK 1 S: in progress; WEEK 1 M: in progress; WEEK 1 T: in progress; WEEK 1 W: Done
2.2.0 | SIQ | SALMA | MENNA | BESHO | FOUDA | 2023-02-18 | 2023-02-18 | 0 | 100% | WEEK 1 S: Done
2.2.1 | RTM | BESHO | AML | SALMA |  | 2023-02-23 | 2023-02-23 | 0 | 100% | WEEK 1 T: Done
2.3 | CRS | AMR |  |  |  | 2023-02-18 | 2023-02-18 | 0 | 0% | WEEK 1 S: Done
2.4 | Requirements Review sheet | FOUDA | AML |  |  | 2023-03-24 | 2023-03-31 | 7 | 0
3 | Design
3.1 | Design document | M.H |  |  |  | 2023-03-22 | 2023-03-29 | 7 | 0%
3.2 | Diagram | OMAR |  |  |  | 2023-03-23 | 2023-03-30 | 7 | 0%
3.3 | Design | OMAR |  |  |  | 2023-03-24 | 2023-03-31 | 7 | 0%
4 | Code
4.1 | Code | OMAR |  |  |  | 2023-03-22 | 2023-03-29 | 7 | 0%
5 | Testing
5.1 | Test specs | OMAR |  |  |  | 2023-03-22 | 2023-03-29 | 7 | 0%
5.2 | Test report | OMAR |  |  |  | 2023-03-22 | 2023-03-29 | 7 | 0%
5.3 | Test cases | OMAR |  |  |  | 2023-03-22 | 2023-03-29 | 7 | 0%
5.4 | Bug reports